## Matt
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/18-1/25 | 7 | 4 | 3 | 0 - learning python 0 - setting up personal environment for Django 5 - discussing project ideas | 4 |  |  |  |  | 3 |  | 0 - Continue experimenting with python/django 3 - Start shell Git repository | 3
1/25-2/1 | 8 | 7 | 1 | 0 - learning python 3 - setting up github flat layout 5 - discussing project implementation | 1 |  |  | 6 |  | 1 |  | 0 - Continue experimenting with python 0 - Implement portions of DAL 0 - Implement something else that needs to be done (maybe site) 1 - SPPP work | 6
2/2-2/8 | 4 | 2 | 2 | 3 - some POC DB work, stopped until design review 5 - discussing SPPP and presentation, some design |  |  |  | 2 |  | 2 |  | 3 - Database design and implementation, DAL to connect to DB 5 - Discuss and agree on DB component of project 5 - Ensure user stories on pivotal tracker are sufficient and being executed by the appropriate members of the team | 6
2/9-2/15 | 4 | 3 | 1 | 3 - some more work with DB 3 - data collection functions using scraper 5 - team discussions |  |  |  | 3 |  | 1 |  | 3 - Data Visualization 3 - Data collection scripts 1 - User Story Creation | 6
2/16-2/22 | 4 | 3 | 1 | 3 - POC graph on web page 3 - new geography database populated 5 - team discussions |  |  |  | 3 |  | 1 |  | 2 - Project UML 3 - Fully Populate Geography Database | 6
2/23-3/2 | 6 | 5 | 1 | 2 - Project UML Diagram 3 - Fully Populate city and geography database 5 - team discussions |  |  | 1 | 4 |  | 1 |  | 3 - Separate Data Collect Module 4 - Unit Test Scraper Module Start 4 - Unit Test Data Collection Start | 6
3/3-3/9 | 1 | 0 | 1 | 5 - team meetings | [5 empty] | 1 |  | 3 - Separate Data Collect Module 4 - Unit Test Scraper Module Start 4 - Unit Test Data Collection Start | 6
3/10-3/16 | 6 | 5 | 1 | 4 - Scraper Refactoring and Unit Testing 5 - Team Meetings/Discussions |  |  |  |  | 5 | 1 |  | 4 - Data Collection Refactor 4 - Data Collection Unit Test | 4
3/17-3/23 | 1 | 0 | 1 | 5 - Team Meetings/Discussions | [5 empty] | 1 |  | 4 - Data Collection Refactor 4 - Data Collection Unit Test | 4
3/24-3/30 | 5 | 4 | 1 | 4 - Collect Data Refactor and Unit Testing 5 - Team Discussions |  |  |  |  | 4 | 1 |  | 4 - Scraper Factory | 4
3/31-4/6 | 1 | 0 | 1 | 5 - Team Discussions | [5 empty] | 1 |  | 4 - Scraper Factory | 4
4/7-4/13 | 4 | 3 | 1 | 4 - Fixes for UI changes 5 - Team Discussions |  |  |  |  | 3 | 1 |  | 4 - Scraper Factory | 4
4/14-420 | 4 | 3 | 1 | 4 - Scraper Factory and refactor to use 5 - Team Discussions |  |  |  |  | 3 | 1 |  | 5 - Software Design Document | 3
4/21-4/27 | 5 | 4 | 1 | 4 - Work with team to debug merge conflicts 5 - Team Discussions 5 - Software Design Document |  |  |  |  | 2 | 3

## John
| Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/18-1/25 | 5 | 4 | 1 | 0,5 | 4 |  |  |  |  | 1 |  | 4 | 4
1/25-2/1 | 3 | 1 | 2 | 0,1,5 | 0.5 | 0.5 |  |  |  | 2 |  | 3 | 3
2/1-2/8 | 3 | 1.5 | 0.5 | 1,2,3,5,0 | 1.5 | 0.5 | 0.5 | 0.5 |  | 0.5 |  | 3 | 3
2/8-2/15 | 3 | 3 | 0.5 | 0,2,5 | 2 |  | 0.5 |  |  | 0.5 |  | 3 | 3
2/15-2/22 | 3.5 | 2.5 | 1 | 0,3,5 | 1.5 |  | 0.5 | 1 |  | 0.5 |  | 3 | 3
2/22-3/1 | 3 | 1.5 | 1.5 | 0,5 | 1.5 |  |  |  |  | 1.5 |  | 3 | 3
3/1-3/15 | 4 | 3.5 | 5 | 0,3,5 | 2 |  |  | 1 |  | 0.5
3/15-3/22 | 3 | 3 | 1 | 6,0,3 | 1 |  |  | 1 |  |  | 1
3/22-3/29 | 3 | 3 | 2 | 6,3 | [6 empty] | 3
3/29-4/5 | 2.5 | 2.5 | 0 | 0,3 | 1 |  |  | 1.5
4/5-4/12 | 3 | 3 | 0 | 0 |  |  |  | 3

## Pat
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/18-1/25 | 14 | 13 | 1 | 0 - Learning python 3 - Building and testing BS4 webscraper | 2 |  |  | 10 |  | 1 |  | - Introduce code to compile skills dictionary into a master dictionary - Figure out how to introduce scraping methods for "sponsored" status, date and location - Design code to import into dataframe and save as .csv file in working directory | 13
1/25-2/4 | 14.5 | 13.5 | 1 | 0 - Learning python 3 - Building and testing BS4 webscraper 5 - Group Communication via Slack | 2 |  |  | 10 |  | 1.5 |  | - Figure out how to introduce scraping methods for "sponsored" status, date and location - Figure out how to remove rows with incorrect job titles, or a url that cannot be correctly parsed by BS4 - Figure out how to have the scrape "realize" when its reached the final page (needs to be HTML context-based, cannot work of the URL) | 14
2/4 - 2/11 | 10 | 9 | 1 | 0 - Learning python 3 - Building and testing BS4 webscraper 5 - Group Communication via Slack | 3 |  |  | 5 |  | 1 |  | - Modify scraper so for each job post, BS4 takes information from the job-post specific <div> and not from the entire pages HTML - Solve the "SAS" and "R" string errors cause by drawing HTML from each job-post page - Prevent pages outside of indeed (i.e. reroutes to bank of america's website, etc.) from being scraped (and appropriately incrementing scraping loop) - Add scraper add-on which collects information on each post's "Sponsored" status or "Time-since-posted" status, which are mutually exclusive (watch loop sequencing!)
2/11 - 2/18 | 13 | 12 | 1 | 0 - Learning Django (Backend) 3 - Building and testing BS4 webscraper 5 - Group Communication via Slack | 4 |  |  | 7 |  | 1 |  | - Insert logic which recognizes when the end of the scraping page has been reached - Implement scraping algorithm add-on which captures the average salary of a given given job site per state (on right side of search results screen) - Add cleansing function which removes duplicate job posts caused by the presense of "Sponsored" job posts - Research dictionary approach, i.e. O(1) to map a city/town_state combination to a US FIPS code (for generation of county Choropleth)
2/18 - 2/25 | 15.5 | 14.5 | 1 | 0 - Learning Django (Backend) (Operating scraper (in real-time) using Views) 3 - Building and testing BS4 webscraper 4 - Implement runtime testing (using Python's Timeit module) 5 - Group Communication via Slack | 4 |  | 2 | 8 |  | 0.5 |  | - Figure out how to scrape the side-information on each indeed search (location, salary range, company, job-types) - Implement left-side-information in county and state-level scrapers (job-title) using url build logic that makes use of indeed's advanced search - Implement left-side-information in a county-level scrapers (company name) using url build logic that makes use of indeed's advanced search - Figure out how to implement concurrent requests (for real-time scraping on non-job-skill search) - Experiment with Plotly's offline setting's and see if plotting time can be reduced (online averaging about 25 to 30 seconds)
2/25 - 3/4 | 17.5 | 15.5 | 2 | 0 - Learning Python's (Concurrency and Twistedless modules) for multithreading / concurrent requests 0 - Learning Plotly's Choropleth Visualization Package 2 - Design plotly US County (Job Title) choropleth 3 - Building and testing BS4 webscraper 5 - Group Communication via Slack | 6 |  | 2 | 6 |  | 1.5 |  | - Implement advanced search features (exact string matching for job title) to the original scraper algorithm. - Research how to implement the static choropleth images in a Django template (via views) - Research visualization technique to show different pay range and/or different job types (i.e. full time/ part time) per state per job search
3/4 - 3/11 | 16 | 15 | 1 | 0 - Learning Plotly's Choropleth Visualization Package 2 - Design plotly US County (Company) choropleth 3 - Implement Webscrapers (State/Job Title)(County/Job Title)(County/ Company) in Django 4 - Test different company names for error 5 - Group Communication via Slack | 4 |  | 2 | 8 |  | 1 |  | - Research color and design option for choropleth (taking Plotly's default continuous color scale and splitting at equal intervals to create a color pallet) - Implement Google's reverse geocoding API to account for city_state elements that are non found in the city > FIPS conversion table (i.e. Westfield Airforcebase_MA > Chickapee_MA) - Figure out if mis-titled locations (i.e. when a poster types a state but not a city). Current the scraper's logic is set to print an error, but ignore this information. - Set try block on plotly generations, so if Plotly's server overwhelmed, the program delays again, and trys to push the same data again in 60 seconds.
3/11 - 3/18 | 11 | 10 | 1 | 0 - Learning Plotly's Choropleth Visualization Package 2 - Design plotly US County (Company) choropleth 3 - Implement Webscrapers (State/Job Title)(County/Job Title)(County/ Company) in Django 4 - Test different company names for error 5 - Group Communication via Slack | 2 |  | 2 | 5 |  | 1
3/18-3/24 |  |  | 2 | 0 - Learning Plotly's Choropleth Visualization Package 2 - Design plotly US County (Company) choropleth 3 - Implement Webscrapers (State/Job Title)(County/Job Title)(County/ Company) in Django 4 - Test different company names for error 5 - Group Communication via Slack | 2 |  | 3 | 2 |  | 1
3/25-3/31 |  |  | 1 | 0 - Learning Plotly's Choropleth Visualization Package 2 - Design plotly US County (Company) choropleth 4 - Build python scraper (parsing fixed HTML inputs) 3 - Implement Webscrapers (State/Job Title)(County/Job Title)(County/ Company) in Django 5 - Group Communication via Slack | 4 |  |  |  | 5
4/1-4/7 |  |  | 1 | 0 - Learning Plotly's Choropleth Visualization Package 2 - Design plotly US County (Company) choropleth 3 - Implement Webscrapers (State/Job Title)(County/Job Title)(County/ Company) in Django 4 - Test different company names for error 5 - Group Communication via Slack | 1 |  | 7 | 3 |  | 1
4/8-4/14 |  |  |  | 0 - Learning Plotly's Choropleth Visualization Package 2 - Design plotly US County (Company) choropleth 3 - Implement Webscrapers (State/Job Title)(County/Job Title)(County/ Company) in Django 4 - Test different company names for error 5 - Group Communication via Slack | 1 |  | 1 | 3 |  | 0.5
4/15-4/21 |  |  | 5 | 0 - Learning Plotly's Choropleth Visualization Package 2 - Design plotly US County (Company) choropleth 3 - Implement Webscrapers (State/Job Title)(County/Job Title)(County/ Company) in Django 4 - Test different company names for error 5 - Group Communication via Slack | 3 |  | 0 | 8 |  | 1
4/22-4/28 |  |  | 3 | 0 - Learning Plotly's Choropleth Visualization Package 2 - Design plotly US County (Company) choropleth 3 - Implement Webscrapers (State/Job Title)(County/Job Title)(County/ Company) in Django 4 - Test different company names for error 5 - Group Communication via Slack | 4 |  | 4 | 10 |  | 2

## James
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/18-1/25 | 1 |  | 1 | 5 - finding team, choosing project | [5 empty] | 1 |  | 0 - start learning django | 3
1/25-2/1 | 4 | 3 | 1 | 0 - learning django, pandas/numpy 5 - discussing project implementation | 3 |  |  |  |  | 1 |  | 0 - continue learning pandas/numpy 3 - implement method for preprocessing | 4
2/1-2/8 | 5 | 3 | 2 | 0 - learning pandas/numpy 3 - implementing data scrubbing method 5 - discussing project progress and iteration 0 | 2 |  |  | 1 |  | 2 |  | 0 - understand different parts of django | 4
2/8-2/15 | 4 | 3 | 1 | 0 - learning django architecture 5 - team meetings | 3 |  |  |  |  | 1 |  | 0 - learn plotly 3 - begin using plotly | 5
2/15-2/22 | 3 | 2 | 1 | 0 - learning plotly 5 - team meetings | 2 |  |  |  |  | 1 |  | 3 - build project, edit as necessary 4 - test django build | 4
2/22-3/1 | 4 | 3 | 1 | 4 - testing django build and scraper - checking skill counts 5 - team meetings |  |  |  |  | 3 | 1 |  | 3 - add data visualization using data from db | 5
3/1-3/15 | 8 | 7 | 1 | 0 - learning pandas/plotly/django 3 - data manipulation/visualization - job comparison plot 5 - team meetings | 3 |  |  | 4 |  | 1 |  | 3 - integrate drop-down menus with db | 3
3/15-3/22 | 6 | 5 | 1 | 0 - learning django (model and template integration) 3 - improving job comparison plot 5 - team meetings | 3 |  |  | 2 |  | 1 |  | 3 - finish integrating menus | 3
3/22-3/29 | 7 | 6 | 1 | 3 - integrating menu and db 5 - team meetings 6 - presentation prep | 3 |  |  |  |  | 1 | 2
3/29-4/5 | 3 | 2 | 1 | 3 - clean up menu/db integration |  |  |  | 2 |  | 1
4/5-4/12 | 3 | 2 | 1 | 0 - learning Selenium and PhantomJS | 2 |  |  |  |  | 1
4/12-4/19 | 3 | 3 | 0 | 0 - learning Selenium and PhantomJS | 3
4/19-4/26 | 9 | 7 | 2 | 3 - implementing menu error handling 4 - Selenium tests for menu and error handling 5 - team communication 6 - presentation prep |  |  |  | 3 | 2 | 2 | 2

## Peter
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/18-1/25 | 8 | 7 | 2 |  | 2 | 2 | 3 |  |  | 1 |  |  | 7
1/25-2/1 | 7 | 6 | 1 |  |  | 2 | 4 |  |  | 1 |  |  | 6
2/2-2/8 | 7 | 5 | 3 |  |  | 1 | 3 | 2 |  | 1 |  |  | 6
2/9-2/15 | 5 | 3 | 1 |  |  |  | 1 | 3 |  | 1 |  |  | 4
2/16-2/22 | 6 | 4 | 2 |  |  |  | 1 | 4 |  | 1 |  |  | 5
2/23-3/2 | 5 | 4 | 1 |  |  |  | 1 | 2 | 1 | 1 |  |  | 4
3/3-3/9 | 5 | 3 | 1 |  |  |  | 1 | 3 |  | 1 |  |  | 4
3/10-3/16 | 3 | 2 | 1 | [5 empty] | 3 |  |  |  | 3
3/17-3/23 | 1 | 1 | 2 | [6 empty] | 1 |  |  | 2
3/24-3/30 | 2 | 1 | 1 | [5 empty] | 1 | 1 |  |  | 3
3/31-4/6 | 2 | 3 | 1 | [5 empty] | 1 | 1 |  |  | 2
4/7-4/13 | 3 | 2 | 1 | [5 empty] | 2 | 1 |  |  | 3
4/14-420 | 5 | 3 | 3 | [5 empty] | 2 | 3 |  |  | 5
4/21-4/27 | 1 | 1 | 1 | [6 empty] | 1 |  |  | 1

## Amal
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/18-1/25 | 7 | 6 | 1 | 0 - refreshing Django and MVC concepts 0 - setting up environment for Django and the project in Visual Code 5 - discussing project ideas 5 - Adding points to SPPP document and | 4 |  |  |  |  | 2 |  | 0 - Continue wokring with django 4 - start figuring out testing packages and methods | 7
1/25-2/1 | 6 | 5 | 1 | 0 - refreshing Django and MVC concepts along with Plotly for visualization 3 - Working with github and git through Visual Code 5 - Discussing project implementation 5 - Added points to SPPP document and to the presentation | 2 |  |  | 2 |  | 1 |  | 0 - Continue Django work 5 - SPPP work 4 - start figuring out testing packages and methods | 6
2/2-2/8 | 6 | 4 | 2 | 3 - started on the visualization work 4 - determining different testing packages and testing cases 5 - discussing SPPP and presentation |  |  |  | 3 | 2 | 1 |  | 3 - Generate graphs in plotly | 6
2/9-2/15 | 4 | 3 | 1 | 3 - worked on more visualization work 3 - basic UI implementation 5 - discussing SPPP and presentation |  |  |  | 3 |  | 1 |  |  | 4
2/16-3/1 | 10 | 8 | 2 | 3 - implemented visualizations for the demo 2 - improved UI implementation 5 - discussing SPPP and iteration 1 presentation |  |  | 2 | 6 |  | 2 |  | 4 - write test cases | 10

## Siwei He
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/18-1/25 | 7 | 4 | 3 | 0 - learning python 5 - discussing project ideas | 4 |  |  |  |  | 3 |  | 0 - keep learning django | 4
1/25-2/1 | 5 | 4 | 1 | 0 - learning python 5 - discussing project implementation | 4 |  |  |  |  | 1 |  | 0 - Keep learning django 3 - SPPP work | 5
2/2-2/8 | 6 | 4 | 2 | 0 - learning python 5 - discussing SPPP and presentation, some design | 4 |  |  |  |  | 2 |  | 0 - Keep learning django 3 - SPPP work | 8
2/9-2/15 | 9 | 8 | 1 | 0 - learning python and Google Chart 3 - update SPPP 5 - team discussions | 4 |  |  | 4 |  | 1 |  | 0 - Keep learning django 1 - User Story Creation | 6
2/16-2/22 | 5 | 4 | 1 | 0 - learning python and Google Chart 5 - team discussions | 4 |  |  |  |  | 1 |  | 0 - learning Django 3 - deal with map create | 4
2/23-3/2 | 9 | 8 | 1 | 0 - learning ploting and Shapefile 3 - implement map with count of jobs by hardcode 5 - team discussions | 4 |  |  | 4 |  | 1 |  | 0 - learning Django 3 - deal with map create | 4
3/3-3/9 | 9 | 8 | 1 | 0 - learning ploting and Shapefile 3 - implement map with count of jobs by hardcode 5 - team discussions | 4 |  |  | 4 |  | 1 |  | 0 - learning Django 3 - deal with map create | 4
3/10-3/16 | 9 | 8 | 1 | 0 - learning ploting and Shapefile 3 - implement map with count of jobs by hardcode 5 - team discussions | 4 |  |  | 4 |  | 1 |  | 0 - learning Django 3 - deal with unit test | 2
3/17-3/23 | 7 | 6 | 1 | 0 - learning ploting and Shapefile 3 - implement collect data unit tests 5 - team discussions | 4 |  |  | 2 |  | 1 |  | 0 - learning Django 3 - deal with unit test | 2
3/24-3/30 | 5 | 4 | 1 | 0 - learning ploting and Shapefile 3 - implement collect data unit tests 5 - team discussions | 2 |  |  | 2 |  | 1 |  | 0 - learning Django 3 - deal with unit test | 2
3/31-4/6 | 3 | 2 | 1 | 0 - learning ploting and Shapefile 3 - implement collect data unit tests 5 - team discussions | 2 |  |  |  |  | 1 |  | 0 - learning Django | 2
4/7-4/13 | 3 | 2 | 1 | 0 - learning GeoDjango 5 - team discussions | 2 |  |  |  |  | 1 |  | 0 - learning Django | 2
4/14-4/20 | 3 | 2 | 1 | 0 - learning GeoDjango 5 - team discussions | 2 |  |  |  |  | 1 |  | 0 - learning Django | 2

## Midterm Contribution Report
StudentName | Requirement Analysis on Pivotaltracker | SPPP Document | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Matthew Scott | Database Prepopulation Skill Bar Chart by Region and Job Title Indeed.com POC All iteration 2 user stories | Management Plan section | Patterns section |  | UML Class Diagram | Skill Bar Chart by Region and Job Title Database prepopulated |  |  | Some meeting minutes
Patrick Ryan | Job Skill Scraping Program (.py) Job Title Scraping Program (US States)(.py) Job Title Scraping Program (US Counties)(.py) Company Name Scraping Program (US Counties)(.py) Supporting .csv / ,xls for Job Title Scraping Programs User Stories (from Homework 2) |  |  |  | First Presentation: Writing and Formatting Second Presentation: Formatting |  | Manual testing of runtime (via Python's Timeit Module) | GitHub branch + commits | Some meeting minutes
John Staley | develop UI, req analysis | req analysis |  |  | iteration 2,3 | homepage, load screen in development | n/a | GitHub branch + commits | slack, meeting minutes
James Christensen | data preprocessing |  |  |  |  | preprocessing | Manual testing of scraper, django build | GitHub branch + commits | meeting minutes
Peter DiMaria | Backend Development Framework Management |  |  |  | Implementation Stack | Backend
Amal Krishna | User Interface Unit Testing
Siwei He | Job By Region(US State) and Skill | Configuration | [6 empty] | Some meeting minutes

## Final Contribution Report
StudentName | Requirement Analysis on Pivotaltracker | SPPP Document | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Matthew Scott | Iteration 3 User Stores (minus Robot Frame work Integration) |  | Initial Version (minus Patterns section) | Initial Version | Some Initial Slides Present on Refactoring | Scraper Refactor (factory pattern) Move DisplayData to Site and give Views instance of PlotGenerator | Scraper Module CollectData Module |  | Help with UI update integration issues
Amal Krishna | Deployment User Interface Selenium Integration test cases Integration from dev to master |  |  |  | Added testing slides for the presentation
James Christensen | Job Comparison Plot |  |  |  | Security and project management slides | Job Comparison Plot Menu and DB Integration | Selenium Tests
Patrick Ryan | Job Skill Scraping Program (.py) Job Title Scraping Program (US States)(.py) Job Title Scraping Program (US Counties)(.py) Company Name Scraping Program (Unused)(.py) Supporting .csv / ,xls for Job Title Scraping Programs User Stories (from Homework 2) Choropleth Pages (Django) |  |  |  | Formatting for Final Presentation, and Presenter of Walkthru for Final Presentation |  | Unit Test for Primary Scraper (Used, but Replaced by Amal's Testing) | Deployment of Primary Scraper and Choropleth Page Visualizations
Siwei He | Job By Region(US State) and Skill | [5 empty] | CollectData
Peter DiMaria | Backend Development Framework Management Django Architecture and Management Front-end Consultation |  |  |  | Framework, Django Architecture, Project Layout | Backend/Database/Views | Views testing between front-end and back-end